## Requirements
Requirement | Where it usually comes from | Our plan | Status | Done | 5
Plan review and permit before building | Health department | Submit drawings and equipment list | Done | Still to do | 10
Handwashing sinks, hot and cold water, soap, towels | Food code as adopted locally | Two: prep area and dish area | Done
Three-compartment sink for washing, rinsing, sanitizing | Food code as adopted locally | With drainboards each side | Ordered | Rules vary by city, county and state: your health department's plan review guide is the list that counts.
Separate food prep sink | Health department | By the prep table | Ordered
Mop or utility sink | Health department | In the back hall | Planned
Grease interceptor | Plumbing code and the city | Under the three-compartment sink | Planned
Hot water enough for washing and handwashing | Plumbing code, food code | Upgrade to a larger heater | Planned
Hood, fire suppression and make-up air over cooking | Fire and mechanical codes | Over the range and steamer | Quoted
Floors, walls and ceilings smooth and cleanable | Food code; 21 CFR 117.20 for manufacturers | Sealed concrete, coved base, wall panels | Quoted
Shielded lighting over food areas | Food code as adopted locally | Shatter-resistant fixtures | Planned
Cold holding at 41°F or below, with thermometers | Food code as adopted locally | Two reach-in coolers and a walk-in | Ordered
Dry storage off the floor | Food code as adopted locally | Shelving 6 inches up | Done
Restroom not opening into food areas | Building code, health department | Existing, with a self-closing door | Done
Pest control plan | Health department | Monthly service | Planned
Zoning and business license | City and county | Light industrial zone | Done

## Build-out budget
Item | Cost | Paid
Plan review fee and permits | 1200
Handwashing sinks, two, installed | 1600
Three-compartment sink with drainboards | 2200
Prep sink | 900
Mop sink | 700
Grease interceptor | 4500
Water heater upgrade | 3500
Hood with fire suppression | 18000
Make-up air | 6000
Floors: sealed concrete, coved base | 7200
Washable wall and ceiling panels | 4800
Shielded lighting | 1800
Walk-in cooler, used, and reach-ins | 6000
Dry storage shelving | 900
Restroom upgrades | 2500
Total | 61800 | 0
Still to pay | 61800

## Read me
Commercial kitchen requirements checklist
From the article: https://www.tarostack.com/articles/commercial-kitchen-requirements
Requirements: each requirement a small commercial kitchen commonly has to meet, where it usually comes from, your plan and its status, with a count of what's done. Rules vary by city, county and state; add what your health department's plan review guide asks for.
Build-out budget: each item's cost and what's been paid; the total and what's still to pay fill in.
The example is the article's made-up tamale maker's 600-square-foot kitchen. The costs are examples, not quotes.
Works in Excel (2010 and later), Google Sheets, LibreOffice and Numbers. No macros.
Free to use and change. Made by TaroStack, inventory and production software for small producers: https://www.tarostack.com