## Opening timeline
Opening day | 2025-09-06
Step | Weeks before opening | Due | Cost | Done | Status
Location chosen, lease signed (deposit and first month) | 26 | 2025-03-08 | 9000 | 2025-03-03 | On time
Business plan and money raised | 26 | 2025-03-08 | 0 | 2025-03-03 | On time
Business name and sales tax permit | 16 | 2025-05-17 | 0 | 2025-06-09 | Late
Coolers, freezers, walk-in and meat case ordered | 16 | 2025-05-17 | 90000 | 2025-05-12 | On time
Shelving and checkouts ordered | 14 | 2025-05-31 | 25000 | 2025-05-26 | On time
Build-out and signs | 12 | 2025-06-14 | 30000 | 2025-07-28 | Late
Food establishment permit applied for | 10 | 2025-06-28 | 2500 | 2025-06-30 | Late
SNAP authorization applied for | 8 | 2025-07-12 | 0 | 2025-07-14 | Late
Wholesaler account opened; opening order planned | 8 | 2025-07-12 | 0 | 2025-07-07 | On time
Registers, scales and inventory system set up | 6 | 2025-07-26 | 8000 | 2025-07-28 | Late
Scales inspected | 4 | 2025-08-09 | 0 |  | Overdue
Staff hired and trained | 4 | 2025-08-09 | 0 | 2025-08-11 | Late
Opening inventory delivered and counted | 1 | 2025-08-30 | 70000 | 2025-08-30 | On time
Permit inspection passed | 1 | 2025-08-30 | 0 | 2025-08-18 | On time
Working cash in the bank | 0 | 2025-09-06 | 50000 | 2025-08-29 | On time
Soft opening | 0 | 2025-09-06 | 0 | 2025-09-06 | On time
Total to start |  |  | 284500
Steps overdue |  |  | 1
Formulas:
Due = B1-[Weeks before opening]*7
Status = IF([Done]<>"",IF([Done]<=[Due],"On time","Late"),IF(TODAY()>[Due],"Overdue","To do"))

## SNAP stocking
Staple food category | Varieties stocked | Units of each (lowest) | Perishable varieties
Vegetables or fruits | 9 | 4 | 6
Dairy products | 7 | 3 | 5
Meat, poultry or fish | 8 | 3 | 6
Breads or cereals | 10 | 4 | 1
Meets the varieties (7 in each)? | Yes
Meets the units (3 of each)? | Yes
Perishables in 3 categories? | Yes
SNAP's Criterion A: at least 7 varieties in each of the 4 staple categories, 3 stocking units of each, and perishables in 3 categories (7 CFR 278.1(b)(1)).

## Read me
How to open a small grocery store: opening timeline
From the article: https://www.tarostack.com/articles/how-to-open-a-small-grocery-store
Opening timeline: each step with the weeks before opening it's due, the due date counted back from the opening day, the cost and the date done; the status shows on time, late, to do or overdue, and the total to start adds up.
SNAP stocking: varieties, units and perishables in each staple category, checked against Criterion A.
The example is the article's made-up small-town grocery. This is a planning template, not legal advice.
Works in Excel (2010 and later), Google Sheets, LibreOffice and Numbers. No macros.
Free to use and change. Made by TaroStack, inventory and production software for small producers: https://www.tarostack.com