## Opening timeline
Opening day | 2027-03-06
Step | Weeks before opening | Due | Cost | Done | Status
Wax, wick and fragrance chosen; wicks with lead-free cores | 12 | 2026-12-12 | 180 |  | To do
Burn tests: each jar size, each scent, full burns logged | 10 | 2026-12-26 | 120 |  | To do
Business name and state tax license | 8 | 2027-01-09 | 20 |  | To do
Product liability insurance | 6 | 2027-01-23 | 450 |  | To do
Labels: name, net weight, your name and address, safety warnings | 6 | 2027-01-23 | 300 |  | To do
Jars, lids and boxes, first order | 5 | 2027-01-30 | 620 |  | To do
Wax and fragrance oil, first order | 5 | 2027-01-30 | 680 |  | To do
Prices set: cost a candle, direct and wholesale | 4 | 2027-02-06 | 0 |  | To do
First pour, cured before sale | 2 | 2027-02-20 | 0 |  | To do
Market stall booked, or shop page live | 2 | 2027-02-20 | 50 |  | To do
First sale | 0 | 2027-03-06 | 0 |  | To do
Total to start |  |  | 2420
Federal rules: a net weight label for the candle (16 CFR 500) and a ban on candlewicks with more than 0.06% lead in a metal core (16 CFR 1500.17(a)(13)).
Formulas:
Due = B1-[Weeks before opening]*7
Status = IF([Done]<>"",IF([Done]<=[Due],"On time","Late"),IF(TODAY()>[Due],"Overdue","To do"))

## Read me
How to start a candle business: launch checklist
From the article: https://www.tarostack.com/articles/how-to-start-a-candle-business
Launch checklist: each step with the weeks before your first sale it's due, the due date counted back, the cost and the date done; the status shows on time, late, to do or overdue, and the total to start adds up.
Costs are examples to replace with your own quotes.
Works in Excel (2010 and later), Google Sheets, LibreOffice and Numbers. No macros.
Free to use and change. Made by TaroStack, inventory and production software for small producers: https://www.tarostack.com