## Opening timeline
Opening day | 2027-04-03
Step | Weeks before opening | Due | Cost | Done | Status
Path chosen: retail-exempt shop, inspected kitchen or co-packer | 16 | 2026-12-12 | 0 |  | To do
Recipe and process tested: marinade, cook, dry | 14 | 2026-12-26 | 200 |  | To do
HACCP training for whoever writes the plan | 12 | 2027-01-09 | 500 |  | To do
HACCP plan with support for the cook and the drying | 10 | 2027-01-23 | 0 |  | To do
Inspected kitchen agreement and deposit | 10 | 2027-01-23 | 250 |  | To do
Label: generic approval, or submitted if it makes special claims | 8 | 2027-02-06 | 0 |  | To do
Water activity test from a lab | 8 | 2027-02-06 | 150 |  | To do
Bags, oxygen absorbers and labels | 6 | 2027-02-20 | 700 |  | To do
Product liability insurance | 4 | 2027-03-06 | 900 |  | To do
First run: kitchen day, beef and marinade | 1 | 2027-03-27 | 1350 |  | To do
First sale | 0 | 2027-04-03 | 0 |  | To do
Total to start |  |  | 4050
Jerky sold beyond your own retail counter is made under federal or state inspection, with a written HACCP plan; a retail store may make it from inspected meat for its own household customers.
Formulas:
Due = B1-[Weeks before opening]*7
Status = IF([Done]<>"",IF([Done]<=[Due],"On time","Late"),IF(TODAY()>[Due],"Overdue","To do"))

## Read me
How to start a jerky business: launch checklist
From the article: https://www.tarostack.com/articles/how-to-start-a-jerky-business
Launch checklist: each step with the weeks before your first sale it's due, the due date counted back, the cost and the date done; the status shows on time, late, to do or overdue, and the total to start adds up.
Costs are examples to replace with your own quotes. This is a planning template, not legal advice.
Works in Excel (2010 and later), Google Sheets, LibreOffice and Numbers. No macros.
Free to use and change. Made by TaroStack, inventory and production software for small producers: https://www.tarostack.com