## Opening timeline
Opening day | 2026-06-01
Step | Weeks before opening | Due | Cost | Done | Status
Process authority review, three recipes (pH and process for each) | 16 | 2026-02-09 | 600 | 2026-02-02 | On time
Acidified foods school for the supervisor | 14 | 2026-02-23 | 450 | 2026-02-19 | On time
Licensed kitchen lined up (own or shared) | 12 | 2026-03-09 | 0 | 2026-03-05 | On time
State food processing license | 10 | 2026-03-23 | 0 | 2026-03-20 | On time
Labels: name, net weight, ingredients, allergens, who made it, nutrition facts unless exempt, barcode | 8 | 2026-04-06 | 500 | 2026-04-02 | On time
FDA registration, Form 2541 (within 10 days of first processing at the latest) | 6 | 2026-04-20 | 0 | 2026-04-14 | On time
Process filings, Form 2541e: each product in pint jars | 5 | 2026-04-27 | 0 | 2026-04-24 | On time
Process filing, Form 2541e: dill spears in quart jars | 5 | 2026-04-27 | 0 | 2026-05-20 | Late
Jars and lids, first order | 4 | 2026-05-04 | 900 | 2026-04-30 | On time
Product liability insurance | 4 | 2026-05-04 | 600 | 2026-05-01 | On time
First licensed batch | 2 | 2026-05-18 | 350 | 2026-05-15 | On time
First store delivery | 0 | 2026-06-01 | 0 |  | Overdue
Total to start |  |  | 3400
Shelf-stable pickles are acidified foods: file each product, in each container size, with FDA before packing it (21 CFR 108.25(c)(2)).
Formulas:
Due = B1-[Weeks before opening]*7
Status = IF([Done]<>"",IF([Done]<=[Due],"On time","Late"),IF(TODAY()>[Due],"Overdue","To do"))

## Read me
How to start a pickle business: from market jars to stores
From the article: https://www.tarostack.com/articles/how-to-start-a-pickle-business
Launch checklist: each step with the weeks before your first store delivery it's due, the due date counted back, the cost and the date done; the status shows on time, late, to do or overdue, and the total to start adds up.
The example is the article's made-up Wisconsin pickle maker. Costs are examples; license fees vary by state. This is a planning template, not legal advice.
Works in Excel (2010 and later), Google Sheets, LibreOffice and Numbers. No macros.
Free to use and change. Made by TaroStack, inventory and production software for small producers: https://www.tarostack.com